## Sheet1
TASK | START DATE | DAYS TO COMPLETE
PROJECT INITIATION | 2024-01-08 | 4
SYSTEM DESIGN | 2024-01-15 | 7
USER INTERFACE DEVELOPMENT | 2024-01-22 | 6
SECURITY IMPLEMENTATION & COMPREHENSIVE DATA MANAGEMENT | 2024-01-29 | 10
PRESCRIPTION GENERATION & MEDICINE PRESCRIPTION | 2024-02-05 | 6
COMPLETE PATIENT HISTORY , CUSTOMIZATION & SCALABILITY | 2024-02-18 | 10
TESTING AND TRAINING | 2024-02-26 | 7
DEPLOYMENT AND EFFICIENCY OPTIMIZATION | 2024-03-04 | 7
DOCUMENTATION , PROJECT REVIEW , CLOSURE | 2024-03-18 | 10